## Read me
Project profitability tracker
Free from Simplify, withsimplify.in/templates/project-profitability-tracker
WHAT IT ANSWERS
What each project actually earned after the fully loaded cost of the people who delivered it, how much of your billable value reached an invoice, and how much of the time you pay for is sold at all.
HOW TO USE IT
1. Rates: one row per person who delivers work. Enter fully loaded cost, not salary: add employer PF, gratuity accrual, insurance, equipment and software. The cost per billable hour is calculated for you, and it will be higher than you expect.
2. Projects: one row per project or retainer. Enter the hours delivered and what you invoiced. Margin, realisation and the variance against your estimate are calculated.
3. Utilisation: billable hours per person per month. Utilisation is calculated against the paid hours on the Rates sheet.
4. Summary: the firm-level picture, including the card rate your margin target actually requires.
Shaded cells are yours to change. Everything else is a formula. The example figures are invented and are there to show the shape; clear them and use your own.
THE TWO RATIOS THAT EXPLAIN MOST OF IT
Utilisation is billable hours as a share of paid hours. It decides how many hours there are to sell.
Realisation is invoiced value as a share of billable value at card rate. It decides how much of each sold hour reaches an invoice, after discounts, write-offs and scope delivered free.
They compound. A firm at 62% utilisation and 82% realisation earns roughly half of what its rate card implies, and neither figure on its own looks alarming.
WHERE THE HOURS COME FROM
This needs time tracked against projects. If you do not track time, start with a fortnight of rough estimates from each person: the answer will be directionally right and better than the rate card.
Count the bench inside paid hours rather than leaving it out, or the cost per billable hour will be understated and every project will look more profitable than it was.
WHAT IT IS NOT
Not a timesheet system, and not a substitute for one if you bill by the hour and need an audit trail. It is a monthly management view.
Not a replacement for your accounts. Invoiced value here is what you billed, which will not tie exactly to recognised revenue on a fixed-price project spanning a year end.
Guide to using this template: withsimplify.in/templates/project-profitability-tracker

## Rates
What an hour of each person costs
Fully loaded cost, not salary. Shaded cells are yours.
Person | Role | Fully loaded cost a year | Paid hours a year | Utilisation | Cost per paid hour | Billable hours | Cost per billable hour | Card rate
Principal | Delivery lead | 2400000 | 1850 | 55% |  |  |  | 4200
Senior engineer 1 | Delivery | 1650000 | 1850 | 65% |  |  |  | 3000
Senior engineer 2 | Delivery | 1600000 | 1850 | 68% |  |  |  | 3000
Engineer 1 | Delivery | 1200000 | 1850 | 70% |  |  |  | 2400
Engineer 2 | Delivery | 1150000 | 1850 | 72% |  |  |  | 2300
Designer | Delivery | 1300000 | 1850 | 60% |  |  |  | 2600
Engineer 3 | Delivery | 1100000 | 1850 | 66% |  |  |  | 2200
Analyst | Delivery | 850000 | 1850 | 58% |  |  |  | 1700
All delivery people
The weighted figures on the total row are what the Projects and Summary sheets use as a blended default.
Cost per billable hour is the number to price from. Cost per paid hour understates it by whatever your utilisation is short of 100%.

## Projects
What each project earned
One row per project or retainer. Shaded cells are yours.
Project | Client | Type | Agreed fee | Est. hours | Hours done | Cost per hour | Card rate | Delivery cost | Value at card rate | Invoiced to date | Margin | Margin % | Realisation | Hours vs est. | Status
Platform rebuild | Client A | Time and materials |  | 1400 | 1460 | 1250 | 2400
Data pipeline | Client C | Time and materials |  | 780 | 810 | 1350 | 2600
Integration work | Client A | Time and materials |  | 380 | 374 | 1150 | 2400
Migration | Client C | Time and materials |  | 560 | 585 | 1100 | 2400
Staff augmentation | Client J | Time and materials |  | 900 | 945 | 1050 | 2200
Mobile app v2 | Client B | Fixed price | 1800000 | 620 | 890 | 1200 | 2400 |  |  | 1800000
Design system | Client E | Fixed price | 950000 | 300 | 400 | 1300 | 2600 |  |  | 950000
Analytics build | Client F | Fixed price | 1250000 | 420 | 520 | 1200 | 2400 |  |  | 1250000
Discovery sprint | Client H | Fixed price | 350000 | 90 | 130 | 1600 | 3000 |  |  | 350000
Reporting module | Client I | Fixed price | 680000 | 210 | 310 | 1150 | 2400 |  |  | 680000
Portal build | Client K | Fixed price | 2200000 | 780 | 1010 | 1180 | 2400 |  |  | 2200000
Support retainer | Client D | Retainer | 1800000 | 700 | 960 | 1050 | 2400 |  |  | 1800000
Growth retainer | Client G | Retainer | 1200000 | 480 | 615 | 1150 | 2400 |  |  | 1200000
Maintenance | Client B | Retainer | 900000 | 380 | 500 | 1000 | 2200 |  |  | 900000
All projects
Status is a rough flag, not a judgement. Review means delivery margin under 35% or realisation under 80%. Watch means under 45% or under 90%. Set the thresholds to whatever your business actually runs at.
Realisation compares what you invoiced against what the hours were worth at card rate. Below 100% means discounts, write-offs or scope delivered free.
On fixed-price work it can read above 100%, which means the job came in under the hours and earned more than your card rate would have. That is real information rather than an error, and it is the other half of the same story as an overrun.
Hours vs estimate matters most on fixed-price work. A consistent overrun is an estimating problem rather than a pricing one, and the two have different fixes.
For time and materials work leave the agreed fee blank. There is nothing to compare against.

## Utilisation
Billable hours by person, by month
April to March. Shaded cells are yours.
Person | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total billable | Paid hours | Utilisation
| 80 | 86 | 92 | 75 | 89 | 82 | 86 | 90 | 70 | 88 | 91 | 90
| 94 | 102 | 108 | 88 | 105 | 97 | 101 | 106 | 82 | 104 | 107 | 106
| 99 | 107 | 113 | 92 | 110 | 102 | 106 | 111 | 86 | 109 | 112 | 111
| 101 | 110 | 117 | 95 | 113 | 105 | 109 | 114 | 88 | 112 | 115 | 114
| 104 | 113 | 120 | 98 | 117 | 108 | 112 | 118 | 91 | 115 | 119 | 118
| 87 | 94 | 100 | 81 | 97 | 90 | 93 | 98 | 76 | 96 | 99 | 98
| 96 | 104 | 110 | 90 | 107 | 99 | 103 | 108 | 83 | 106 | 109 | 108
| 84 | 91 | 97 | 79 | 94 | 87 | 90 | 95 | 73 | 93 | 96 | 95
Team
Paid hours are pulled from the Rates sheet, so a change there flows through here.
Billable means an hour a client is charged for, whether or not it was eventually invoiced. What happened to it afterwards is realisation, on the Projects sheet.
A month well below the rest usually has an explanation worth writing down: a project ended, someone was on the bench, or a proposal took a fortnight.

## Summary
The firm this year
Everything here is calculated. The two shaded cells are yours.
DELIVERY
Invoiced to date |  | What you billed across every project
Value at card rate |  | What the same hours were worth before discounts and free scope
Realisation |  | The share of your billable value that reached an invoice
Delivery cost |  | Hours delivered at fully loaded cost
Gross margin
Gross margin % |  | Before anything that is not delivery
THE WHOLE FIRM
Overheads, share of revenue | 25% | Sales, admin, finance, office and founder time
Operating margin you want | 20% | Used to work the required card rate backwards
Overhead cost
Operating profit
Operating margin % |  | The number the target above is measured against
CAPACITY
Utilisation across the team |  | Billable hours as a share of the hours you pay for
Hours paid for
Hours billed
Hours you could not sell
What those hours cost |  | At the weighted cost of a paid hour
Value never invoiced |  | Discounts, write-offs and scope delivered free
WHAT THE TARGET NEEDS
Cost per billable hour |  | Weighted across the team
Left for delivery after overheads and margin |  | If this is zero or less, no rate card can reach the target
Effective rate the target needs |  | After realisation has taken its share
Card rate the target needs |  | Divide by realisation to get back to the card
Your card rate now |  | Weighted across the work you actually delivered
Headroom on the card rate |  | Negative means the card rate is below what the target requires
DOES IT TIE?
Hours on the Projects sheet |  | Hours recorded against projects
Hours on the Utilisation sheet |  | Billable hours recorded by person
Difference
Check |  | Delivery cost comes from Projects and hours billed from Utilisation. If these two do not agree, every margin on this sheet is wrong.
HOW TO READ THIS
If the card rate has no headroom, fix realisation before raising prices. Billing work you already deliver is faster and less contentious than charging more for it.
Compare the two loss figures under Capacity. Whichever is larger tells you whether the problem is selling hours or billing them, and they have completely different fixes.
Utilisation below about 60% across a team usually means resourcing rather than effort: people are between projects, not idle at their desks.
A healthy average can sit on top of two or three projects that lose money. Sort the Projects sheet by margin before concluding anything from this page.
Every figure on this sheet comes from the other three. If something looks wrong, the input is wrong.